## Sheet1
Use Case | Implementation Status (As per User Stories & Acceptance Criteria) | Validation Gaps / Items Pending Verification | Observations and Remarks
Access Authorized Chatbot Interface | This use case cannot be validated because the chatbot is currently not integrated with any university portal. | To validate this use case, the chatbot needs to be integrated with an internal university portal or system. | • Admin is receiving different responses. • There is no separate login available for Staff; clarification is required on whether Staff belong to the Faculty group. • It is unclear what the term “steps” indicates. The mobile responsiveness is not as expected - for the platform/tool
Retrieve Authorized Information | Not fully validated. | Several acceptance criteria require verification. | UIB-18 • Point 4 – Session expiry functionality needs to be verified. UIB-23 • Point 5 – The approved list of documents change log/analytics is not displayed. • Point 6 – Needs validation under technical issue or outage conditions. • Point 7 – The chatbot does not automatically provide responses; further testing is required. • Point 2 – Restricted information is not shown, but the chatbot displays sources or citations for those documents, which ideally should not happen. UIB-27 • Point 3 – Source-system permissions (portal/KB/Confluence/Jira ACLs) should be respected and not bypassed; verification is required. • Point 4 – Permission-checking error handling needs validation. UIB-31 • Point 2 – The chatbot does not generate answers from restricted sources but displays the source title and details. • Point 3 – Details of restricted documents are shown. • Point 5 – Error handling during answer generation needs verification. • Point 7 – Requires testing with additional queries. • Point 8 – Responses are not organized or summarized; they appear as paragraphs. For unauthorized queries, a generic message is shown instead of a specific one. • Point 9 – Only the source/document name is shown; the following details are missing: – High-level location (repository/folder/space) – Version/date – Deep links only for authorized documents – Unauthorized documents should not appear in the sources list, but they are currently visible. UIB-35 • Page numbers are displayed for all answers, but proper citations are not shown. • This occurs for both authorized and unauthorized documents. • Point 5 – Documents that are not accessible to the user are still listed in visible citations. • Point 7 – Citation format differs from the expected format.
UIB-35 • Page numbers are displayed for all answers, but proper citations are not shown. • This occurs for both authorized and unauthorized documents. • Point 5 – Documents that are not accessible to the user are still listed in visible citations. • Point 7 – Citation format differs from the expected format.
Enforce Document-Level Access Control | Not fully validated. | Multiple validation checks are pending. | UIB-40 • Point 6 – Chatbot responses for timeout issues or errors need verification. • Point 7 – A list of restricted documents is displayed but should not be visible to end users. UIB-44 • The chatbot provides a neutral message for unauthorized/restricted documents but still displays citations. • Point 3 – This behavior is not working as expected. • Point 4 – When there are no matching documents or when documents are restricted, the chatbot displays a neutral message but still shows sources with matching keywords. UIB-48 • Needs verification. UIB-52 • Needs verification.
Retrieve Latest Document Version | Not validated. | Validation pending. | • No observations recorded yet.
Handle Multiple Relevant Documents | Not validated. | Validation pending. | • No observations recorded yet.
Maintain Conversational Context | Partially implemented. Feature 4 – Session context within active chat (UIB-93). | Some acceptance criteria require further verification. | UIB - 93 • Point 1 – The chatbot maintains conversational context and provides responses accordingly. • Point 4 – Needs verification. • Point 5 – Needs verification. • Point 6 – Requires validation. • Point 7 – This functionality is not currently covered.
Reset Context on New Session | Not validated. | Validation pending. | • No observations recorded yet.
Clarify Ambiguous or Broad Queries | Not validated. | Validation pending. | • No observations recorded yet.
Handle No Matching Content | Not validated. | Validation pending. | • No observations recorded yet.
Escalate Unanswered Queries | Not validated. | Validation pending. | • No observations recorded yet.
Provide Informational Guidance for Forms | Not validated. | Validation pending. | • No observations recorded yet.
Prevent Workflow Execution | Not validated. | Validation pending. | • No observations recorded yet.
Handle Irrelevant Queries | Not validated. | Validation pending. | • No observations recorded yet.
Enforce Abuse and Security Guardrails | Not validated. | Validation pending. | • No observations recorded yet.
Capture User Feedback | Not validated. | Validation pending. | • No observations recorded yet.
Admin Console | Partially implemented. Feature 8 – PDF format supported (UIB-482). Feature 1: Role & Persona Management - Need to validate UIB -188 Feature 2: Repository Connector Setup (Cloud vs Drive) - Not Implemented Feature 3: Indexing & Sync Controls - Need to check the Manual Run Sync UIB -196 Feature 4: Session & Experience Controls - Not Implemented Feature 5: Fallback & User Messaging - Not Implemented Feature 6: Escalation Routing & Notifications - Not Implemented Feature 7: Branding & UI Theming - Not Implemented Feature 8: Allowed File Formats & Content Processing - Partially Implemented - PDF format supported Feature 9: Connector Settings & Governance - Not Implemented Feature 10: Analytics & Logging Dashboard - Not Implemented | Multiple validation gaps identified. | UIB - 482 • Point 1 – No option is available to toggle supported file formats; only PDF files are accepted. Uploading other formats results in an error. • Point 2 – Needs verification. • Point 3 – Requires testing with other formats such as images, Excel, etc. • Point 4 – The UI does not indicate the maximum file size, and there is no functionality for the admin to reset it. The system accepts even a 200MB PDF file. • Point 5 – An option exists to upload approved documents, but there is no functionality to differentiate approved and unapproved documents or to identify the latest version for content extraction. • Point 6 – This functionality is not covered. • Point 7 – This functionality is not covered. UIB - 188 * Point 2 - is compeltely implemented * Point 1, 3, 4 - Need to be implemented * When ever the keywords of the query is matched to any of the documents, that documents will be listed as sources but accurate information from appropriate docuemnt iis given in the response UIB- 196 * validation Pendingas the functionality is not integrated to the system/platform
Academic Knowledge Search | Partially implemented. Feature 1, 2, 5, 6 – Student/Faculty scoped document retrieval (UIB-514, UIB-519). Feature 4 – Student-safe filtering via RBAC (UIB-529). Feature 7 and 8 – Faculty-only and Admin-only documents hidden by role (UIB-529). | Some validation scenarios require testing. | UIB-514 * When the query is like "Guide me to students Admission and campus services" It will not give the actual answer or information but it will guide the user to navigate in the document and find the answer. * The Response will be given in a single paragraph eventhough the docuemnthas that information in an organized way or bullet points - Not paraphrasing or organising teh responses * While giving the source list it might consider the keyword matching and give all the list of documents which has that keyword given in the query along with the actual document which has the response for the query * When a query is asked combining two informations of two different documents, it will give the response for both the queries in two paragraphs - for outdate version of documents -Need to be impelmented * When a vague/general query is asked like "student" it will ask some follow up question to get the clarity and then respond back -Could you please clarify your question? Are you asking about student admissions, campus services, attendance policies, examination rules, or something else?" but taking more time to give this follow up response UIB - 519 * When we ask any query realted to loactions or acmpus - teh query should be in a proper way like garmatically correct- otherwise , it will not give the response, it wil give the neutral response * While giiving the response for this query "which buildings have the elevators" it will include details about some loactions which does not have elevators * When we ask general query about "Campus" instaed of asking follow up question like which question, It will consolidate the deatisl of multiple campus and give the response UIB - 524 * when the query is generic like "Give the assessment structure" - eventhough multiple documents has that information it is considering only one document by keyword matching and giving the response- It is not consolidating all the information of all the documents UIB - 529 * Covered all the role aware filtering and responses according to the authorized documents