## Internal Chatbot Requirements
UC ID | UC Name | Description | Epic ID | Trigger | Acceptance Criteria | Implementation Status | Gap/Notes
UC-01 | Access Authorized Chatbot Interface via Internal Systems | This epic is about letting logged-in users (Students, Faculty, Staff) open and use the internal chatbot from approved internal systems, portals, or channels. The chatbot should open as a widget or page inside those systems, use the existing organization login (SSO/portal), and respect the user's role (Student/Faculty/Staff). | UIB-2 | User opens an approved internal system/portal and clicks the chatbot widget or entry point. | 1. Chatbot opens as embedded widget or page inside approved internal systems. 2. User identity recognized via existing SSO/portal authentication (no re-login). 3. User role (Student/Faculty/Staff) mapped from authentication context. 4. Chatbot session starts on user trigger (click on button/widget/page). 5. Chatbot respects role-based permissions throughout the session. | ✅ Done | Auth (JWT), login UI, role mapping implemented
UC-02 | Retrieve Authorized Information via Internal Chatbot | This epic is about allowing logged-in users (Students, Faculty, Staff) to ask questions in natural language in the chatbot and get answers only from internal, approved knowledge sources. The chatbot must respect each user's role and permissions, use only content they are allowed to see, and show links only to documents they can open. | UIB-22 | User types a natural-language question into the chatbot and submits it. | 1. User can submit natural-language queries without knowing specific system/document names. 2. Chatbot searches only approved internal knowledge sources. 3. Role/group-based permissions applied to filter search results. 4. Response generated only from content user is authorized to see. 5. Citations and links shown only for documents user can open. | ✅ Done | RAG pipeline, RBAC filtering, citation extraction implemented
UC-03 | Enforce Document-Level Access Control | This epic is about making sure the chatbot never exposes restricted documents or their details. When a user submits a query that matches restricted content, the chatbot must: Search only in approved sources. Return answers only from documents the user is allowed to see. Respond with a neutral message if no authorized documents are available. Never reveal restricted titles, locations, snippets, or the existence of restricted documents. | UIB-39 | User submits a query that matches restricted or access-controlled content. | 1. Chatbot filters results to documents the user is authorized to access. 2. Neutral response returned when only restricted documents match. 3. Safe next steps optionally suggested when no accessible info found. 4. Restricted document titles, locations, snippets, or existence never revealed. | ✅ Done | Two-layer RBAC enforcement (API route + chunk retrieval)
UC-04 | Retrieve Latest Document Version | This epic is about making sure the chatbot uses only the current, approved version of documents when answering user queries. When Admins enable governed 'current/approved' retrieval, the chatbot will: Use only the current, approved version from connected repositories. Ignore drafts, archived, or superseded versions based on configured rules. Show which version it used (document name + version/effective date + link). | UIB-56 | Admin enables governed current/approved retrieval mode; user submits a query. | 1. Admin can enable governed 'current/approved' retrieval mode. 2. Only current, approved document versions used in answers. 3. Drafts, archived, and superseded versions ignored. 4. Exact version cited (name + version/effective date + link). | ⚠️ Partial | Basic retrieval works; version governance config not fully implemented
UC-05 | Handle Multiple Relevant Documents | This epic defines how the chatbot behaves when more than one relevant document matches a user's query. The chatbot should: Collect multiple authorized, current documents. Consolidate insights from those documents into a clear answer. Cite multiple sources where applicable. Avoid confusion or leakage from restricted or outdated content. | UIB-74 | User submits a query that matches more than one relevant, authorized document. | 1. All relevant, authorized, current documents collected for the query. 2. Insights consolidated from multiple documents into one clear answer. 3. Citations from multiple documents shown where applicable. 4. Guidance provided when many documents are relevant (refine question). 5. No confusion or leakage from restricted or outdated content. | ⚠️ Partial | Multi-doc retrieval via RAG; explicit consolidation UX not fully tested
UC-06 | Maintain Conversational Context | This epic defines how the chatbot maintains context within an active session, so that users can ask follow-up and refinement questions without repeating previous details. | UIB-92 | User asks a follow-up or refinement question within the same chat session. | 1. Key details remembered within current session for follow-up questions. 2. User can clear or reset context manually within a session. | ✅ Done | Session-based context in agent.py
UC-07 | Reset Context on New Session | This epic ensures that when a new session begins or an existing session expires, previous conversational context is cleared, and the chatbot starts a fresh conversation. | UIB-102 | User session expires, user logs out, or user starts a new session. | 1. Context cleared when session expires or user logs out. 2. Fresh context started on new session start. 3. Old context does not carry over to new conversations. | ✅ Done | Session isolation in agent.py
UC-08 | Clarify Ambiguous or Broad Queries | This epic covers how the chatbot responds when a user's query is unclear, incomplete, or overly broad. The chatbot should prompt for clarification before answering. | UIB-108 | User submits a query that is unclear, incomplete, or overly broad. | 1. Ambiguous or overly broad queries detected before answering. 2. Chatbot asks user for clarification when query is unclear. 3. More accurate answer provided after clarification. | ✅ Done | Prompt-based clarification in ReAct agent template
UC-09 | Handle No Matching Content | This epic defines chatbot behavior when no matching or authorized content exists. The chatbot should provide a clear fallback message and avoid speculative or invented responses. | UIB-122 | User submits a query for which no matching or authorized content exists. | 1. Detected when no matching or authorized content exists. 2. Safe fallback message returned instead of speculative answer. 3. No guessing or invented answers. | ✅ Done | Fallback response logic in agent.py with retry
UC-10 | Escalate Unanswered Queries | This epic defines how unanswered queries are logged and escalated to the appropriate university team, including relevant metadata. | UIB-130 | Chatbot cannot answer a user query after exhausting all retrieval attempts. | 1. Unanswered queries logged with key metadata. 2. Queries routed to designated university teams. 3. Content gaps visible to administrators. | ✅ Done | DynamoDB escalation store + Slack webhook + admin endpoint (11 tests)
UC-11 | Provide Informational Guidance for Forms | This epic covers how the chatbot provides informational guidance about institutional forms (purpose, eligibility, where to find them) based solely on documented information. | UIB-139 | User asks about institutional forms (purpose, eligibility, location). | 1. Chatbot explains purpose and usage of institutional forms. 2. Chatbot guides users on where to find forms. 3. Answers based solely on documented information. | ❌ Pending | No form-specific guidance implemented; handled by general RAG
UC-12 | Prevent Workflow Execution | This epic ensures the chatbot does not submit, complete, or process institutional workflows (like form submissions) and communicates this clearly to users. | UIB-147 | User attempts to submit, complete, or process a form/workflow via the chatbot. | 1. Workflow-execution attempts detected. 2. User informed that workflow execution is not supported. 3. User directed to official systems for form submissions. | ❌ Pending | No explicit workflow-prevention guardrail implemented
UC-13 | Handle Irrelevant Queries | This epic describes how the chatbot responds to queries unrelated to institutional information, politely declining and explaining what it can help with. | UIB-156 | User submits a query unrelated to institutional topics. | 1. Irrelevant or out-of-scope queries detected. 2. Polite decline with scope guidance provided. 3. Chatbot does not attempt to answer as general internet assistant. | ✅ Done | Prompt-based handling in ReAct agent template
UC-14 | Enforce Abuse & Security Guardrails | This epic ensures abusive, harmful, or system-manipulation queries are blocked, logged, and handled according to the university's approved guardrail and security policy. | UIB-165 | User submits an abusive, harmful, or system-manipulation query. | 1. Abusive or harmful queries detected. 2. Blocked or safely responded to according to policy. 3. Security events logged and optionally escalated. | ✅ Done | Two-layer guardrails (sync patterns + LLM classification), 27 tests
UC-15 | Capture User Feedback | This epic lets users provide feedback (rating and optional comment) on chatbot responses, and records it for analysis and quality improvement. | UIB-178 | User clicks thumbs-up/thumbs-down on a chatbot response. | 1. Users can rate chatbot responses (thumbs up/down). 2. Optional free-text feedback captured. 3. Feedback recorded for analysis and quality improvement. | ✅ Done | DynamoDB feedback store + UI buttons + admin endpoint (12 tests)
UC-16 | Admin Console | This epic defines the admin console for configuring and monitoring the chatbot. Admins can manage roles/personas, connectors, indexing, sessions, fallback messaging, escalation, branding, and analytics. | UIB-187 | Admin accesses the admin console to configure or monitor the chatbot. | 1. Role & persona management configurable. 2. Repository connector setup available. 3. Indexing & sync controls provided. 4. Session & experience controls configurable. 5. Fallback & user messaging configurable. 6. Escalation routing & notifications configurable. 7. Branding & UI theming configurable. 8. Analytics & logging dashboard available. 9. Allowed file formats & content processing configurable. 10. Connector settings & governance configurable. | ⚠️ Partial | Admin API endpoints exist; full admin console UI not implemented